## PR -
DIRECTORATE OF AGRICULTURE, JAMMU
Progress Report under Horticulture Mission for North East and Himalayan States (HMNEH) during the year 2014-15 Ending March 2015 of the Approved Action Plan 2013-14
Approved Action Plan 2013-14 |  |  | Rs. 105.77 lakhs.
Funds Released
1st installment |  |  | Rs.27.85 lakhs. |  |  | Date | 21-08-2013
Iind Installment |  |  | Rs.74.41 lakhs |  |  | Date | 21-01-2014
Total |  |  | Rs.102.26 lakhs
Funds Utilized ending March 2014 |  |  | Rs.85.56 lakhs
Funds Utilized ending September 2014 |  |  | Rs. 16.70 lakhs
Total |  |  | Rs.102.26 lakhs
Unspent balance as on 1-04-2015 |  |  | Nil
SNO | Component | Units ha/Nos | Rate of Assistance | Approved Action Plan 2013-14 |  | Targets As per Funds release during 2013-14 |  | Achievement upto Ending March 2014 |  | Achievement during August 2014 |  | Cummulative Achievement up to the month Ending March 2015
|  |  |  | Phy | Fin | Phy | Fin | Phy | Fin | Phy | Fin | Phy | Fin
1 | Area Expansion
Vegetables
| Open Pollinated (Pvt.) | Ha | 0.225 | 45 | 10.125 | 45 | 10.125 | 45 | 10.125 |  |  | 45 | 10.125
| Hybrid | Ha | 0.3375 | 100 | 33.75 | 95.53 | 32.24 | 52.52 | 17.725 | 43 | 14.515 | 95.53 | 32.24
2 | Shade Net Houses | [10 empty] | - | -
| Wooden Structure | Sq. mtrs. | 0.00205 | 2400 | 4.92 | 2400 | 4.92 | 2400 | 4.92 |  |  | 2400 | 4.92
| Anti bird/Anti hail net | Sq. mtrs. | 0.0001 | 20000 | 2 | - | - | - | - |  |  | - | -
3 | Protected Cultivation (Natural Ventilation system)
| Tubular Structure | Sq. mtrs. | 0.00468 | 1000 | 4.67 | 1000 | 4.67 | 1000 | 4.67 |  |  | 1000 | 4.67
4 | Prime Minister's Reconstruction Plan (PMRP) | [10 empty] | - | -
| Creation of water sources | [10 empty] | - | -
| water harvesting System for storage of water in 20*20*3 m tanks/tube well/ dug well | Nos. | 1.03 | 30 | 30.9 | 30 | 30.9 | 28 | 28.78 | 2 | 2.12 | 30 | 30.9
5 | Horticulture Mechanization | [10 empty] | - | -
| Power Machine upto (20 BHP) with rotavator/equipment | Nos. | 0.6 | 4 | 2.4 | 4 | 2.4 | 4 | 2.38 |  | 0.02 | 4 | 2.4
| Power Machine above (20 BHP) including accessories/equipment | Nos. | 1.5 | 10 | 15 | 10 | 15 | 10 | 15 |  |  | 10 | 15
6 | Project Management including additional manpower, project preparation cost, institutional strengthening, hire/purchase of vehicles, hardware. Software etc. |  | - |  | 2 | - | 2 |  | 1.96 |  | 0.04 |  | 2
| TOTAL |  |  |  | 105.77 |  | 102.26 |  | 85.56 |  | 16.695 | - | 102.255
Director of Agriculture
Jammu

## Sheet3
DIRECTORATE of AGRICULTURE JAMMU
Horticulture Mission for North East and Himalayan States, 2014-15
Approved Action Plan 2014-15= Rs. 247.18 Lakhs
Release of Funds |  | Rs. 72.38 Lakhs
Intrest Accrued |  | Rs. 8.98 Lakhs
Total |  | Rs. 81.36 Lakhs
Funds Utilized |  | Rs. 51.7007 Lakhs
%age of Utilization |  | 64%
S.No | DDO,s | Funds Released( In Lakhs) |  |  | Funds Utilized In Lakhs) |  |  | Amountpendimg for drawal
|  | Treasury Drawal | Cheque Drawal | Total | Treasury Drawal | Cheque Drawal | Total
1 | CAO Jammu | 7.226 | 0.7 | 7.926 | 1.1276 | 0.533 | 1.6606 | 5.0154
2 | CAO Samba | 7.4 | 0.2 | 7.6 | 2.65 | 0.2 | 2.85 | 4.75
3 | CAO Kathua | 7.774 | 0.2 | 7.974 | 5.024 | 0.2 | 5.224 | 2.75
4 | CAO Rajouri | 7.8 | 0.7 | 8.5 | 3.25 | 0.7 | 3.95 | 4.543
5 | CAO Poonch | 7.95 | 0.2 | 8.15 | 7.14 | 0.2 | 7.34 | 0
6 | CAO Udhampur | 5.9 | 0.2 | 6.1 | 3.9 | 0.2 | 4.1 | 2
7 | CAO Reasi | 7.13 | 1.2 | 8.33 | 2.68 | 1.2 | 3.88 | 4.45
8 | CAO Ramban | 7.2 | 0.2 | 7.4 | 7.2 | 0.2 | 7.4 | 0
9 | CAO Doda | 6.23 | 0.2 | 6.43 | 4.25 | 0.2 | 4.45 | 1.98
10 | CAO Kishtwar | 6.65 | 0.2 | 6.85 | 5.9 | 0.2 | 6.1 | 0
11 | Joint Director Agriculture (Inputs) |  | 1.85 | 1.85 | 0 | 1.85 | 1.85 | 0
12 | Accounts Officer | 1.12 | 2.8961 | 4.0161 | 0 | 2.8961 | 2.8961 | 1.12
13 | Total | 72.38 | 8.7461 | 81.1261 | 43.1216 | 8.5791 | 51.7007 | 26.6084
Director Agriculture
Jammu

## Sheet5
DIRECTORATE OF AGRICULTURE, JAMMU
Progress Report under Horticulture Mission for North East and Himalayan States (HMNEH) Programme MIDH during the year 2014-15 as on Ending March 2015 of the Approved Action Plan 2014-15, in respect of Agriculture Jammu
| Intrest Earned during 2013-14 | Rs. 8.98 Lakhs | To be Utilized on the Approved Action Plan 2014-15
| Funds Released | Rs. 72.38 Lakhs | GOVERENMENT ORDER NO- 51- Horti. Of 2014, dated 19-11-2014
| Total | Rs. 81.36 Lakhs
| Funds Utilized | Rs. 51.7007 Lakhs
| %age of Utilization | 64%
S. No. | Item | Cost Norms | Pattern of Assistance | Appropved Action Plan 2014-15 |  | Achievement Ending March 2015
|  |  |  | Phy. | Fin | Phy. | Fin
1 | Area Expansion
| Hybrid | Rs. 50,000/= per ha | Rs. 25,000/= Ha | 50 | 12.5 | - | -
2 | Mushroom
| Production Unit | Rs. 20.00 lakh/ unit | Public Sector 100 %, (Rs. 20.00 lacs per no.) | 1 | 20 | - | -
3 | Water Harvesting Structure for individuals for storage of water in 20m*20m*3m ponds/ tube wells/ dug weiis @ Rs. 100/- cum | Rs. 1.80 lakhs / unit in hilly areas | 50 % cost limited to Rs. 90,000 per no. | 10 | 9 | 10 | 7.024
4 | Protected Cultivation
Green House Structure
| Fan & Pad System | Rs. 1897.50 / sq.m up to 500 sq.m | 50% of cost limited to Rs 948.75/=per Sq mt. for a maximum area of 4000 sq. m per beneficiary | 300 | 2.8462 | - | -
Naturally Ventilated System
| Tubular System | Rs. 1060 / sq.m up to 500 sq.m | 50% of cost limited to Rs. 530/= per Sq mt. for a maximum area of 4000 sq. m per beneficiary | 2000 | 10.6 | - | -
| Wooden System | (Rs. 621/ sq.m For hilly areas) | 50% of cost limited to Rs. 310.50/= per Sq mt. for a maximum area of 200 sq. m per beneficiary | 8000 | 24.84 | - | -
| Bamboo System | (Rs. 518/ sq.m For hilly areas) | 50% of cost limited to Rs. 259.00/=per Sq. Mt. for a maximum area of 200 sq. m per beneficiary | 2000 | 5.18 | - | -
5 | Shade Net House
| Tubular System | (Rs. 816/ sq.m For hilly areas) | 50% of cost limited to Rs. 408/= per Sq Mt. for a maximum area of 4000 sq. m per beneficiary | 3000 | 12.24 | - | -
| Wooden System | (Rs. 566/ sq.m For hilly areas) | 50% of cost limited to Rs.283/= per Sq. mt. for a maximum area of 200 sq. m per beneficiary | 3000 | 8.49 | - | -
| Bamboo System | (Rs. 414/ sq.m For hilly areas) | 50% of cost limited to Rs.207/= per Sq. mt.for a maximum area of 200 sq. m per beneficiary | 2700 | 5.589 | - | -
| Anti bird Hail Nets | Rs. 35/= per Sq. m. | 50% of costlimited to Rs. 17.50/= per Sq. mt. for a maximum area of 5000 sq. m per beneficiary | 1000 | 0.175 | - | -
6 | Promotion of Integrated Nutrient Management (INM) Integrated Pest Management (IPM)
| Promotion of IPM/INM | Rs. 4000/= per ha | 30% of cost subject to a maximum area of Rs. 1200/ = / ha limited to 4.00 ha per beneficiary | 500 | 6 | - | -
7 | Organic Farming
| Adoption of organic farming 1st. Year** | Rs.20,000/ha | 50% of cost limited to Rs.10000/ha for a maximum area of 4 ha per beneficiary, spread over a period of 3 yrs involving an assistance of Rs.4000/- in first year and Rs.3000/- each in second & third year . The programme to be linked with certification. | 100 | 4 | - | -
| Organic Certification 1st. Year** | Project based | Rs.5 lakh for a cluster of 50 ha which will include Rs.1.50 lakh in first year, Rs.1.50 lakh in second year and Rs.2.00 lakh in 3rd year. | 1 | 1.5 | - | -
| iii) Vermi Compost Units/organic input production | 50% of the cost confirming to the size of the unit of 30*8*2.5 feets dimension of permanent structure to be adminstered on pro rata basis. | cost limited to Rs 50,000/= per no. conforming to the size of the unit of 30*8*2.5 dimension of permanent structure to be administered on pro-rata basis. For HDPE vermibed, 50% of cost conforming to the size of 96cft (12*4*2) and IS 15907:2010 to be administered on pro-rata basis. | 144 | 72 | 106 | 32.86
8 | Pollination support through beekeeping
| i. Production of bee colonies by bee breeder | Rs.10.00 lakh | 40% of cost for producing min. of 2000 colonies/year | 3 | 12 | - | -
| ii) Honey bee colony | Rs.2000/colony of 8 frames | 40% of cost limited to Rs. 800/=per no. Limited to 50 colonies/beneficiary | 470 | 3.76 | - | -
| iii) Bee Hives | Rs.2000/ per hive | 40% of cost limited to Rs. 800/=per no. Limited to 50 colonies/beneficiary | 470 | 3.76 | 470 | 2.82
| iv) Equipment including honey extractor (4 frame) food grade container (30kg) net, including complete set of Bee keeping equipment. | Rs.20,000/set | 40% of the cost limited to one set per beneficiary | 30 | 2.4 | - | -
9 | Horticulture Mechanization
| i) Tractor (upto 20BHP) |  | Rs. 75,000 per No. | 10 | 7.5 | 7 | 2.25
10 | Human Resource Development (HRD)
i) Training of farmers
| a) within the State | Rs.1000/day per farmer including transport | 100% of the cost | 500 | 5 | - | -
| b) Outside the State | Project based as per actual | 100% of the cost |  | 2 | - | -
ii) Exposure visit of farmers
a) within the State
| b) Outside the State | Project based as per actual | 100% of the cost |  | 3 | - | -
c) Training/study tour of technical staff/field functionaries
| a) within the State | Rs.300/day per participant plus TA/DA, as admissible | 100% of the cost
| b) Study tour to progressive States/units (group of minimum 5 participants) | Rs.800/day per participant plus TA/DA as admissible | 100% of the cost | 100 | 2.8 | - | -
11 | Mission Management
| State & District Mission offices & Implementing agenciesfor administrative expences, Project Prepration / Computerization / Contigency |  |  |  | 3 |  | 2.7
| Institutional Strengthening /hire purchase of vehicle/ Soft ware/ Hardware (Public Sector ) |  |  |  | 3 |  | 1.85
| Techanical Support Group for hiring Experts /Staff/ studies/ monitoring / mass media / publicity /Video confrenceing etc |  |  |  | 4 |  | 2.2
| Total |  |  |  | 247.18 |  | 51.704
Director Agriculture
Jammu

## Sheet7
DIRECTORATE OF AGRICULTURE JAMMU
Horticulture Mission for North East and Himalayan States, 2014-15
Approved Action Plan 2014-15= Rs. 247.18 Lakhs | [5 empty] | Goverenment Order NO. 52- Horti, of 2014 Dated 19/11/2014
Release of Funds |  | Rs. 72.38 Lakhs |  | Goverenment Order NO. 51- Horti, of 2014 Dated 19/11/2014
Intrest Accrued |  | Rs. 8.98 Lakhs |  | letter no. DHK/Plg./Dev/6686-91, dated 11-08-2014
Total |  |  |  | Rs. 81.36 Lakhs
Funds Utilized |  |  |  | Rs. 51.7007 Lakhs
%age of Utilization |  |  |  | 64%
Funds remained unutilized |  |  |  | Rs. 29.6593 Lakhs
Bills remained pending in the treasuries for drawal |  |  |  | Rs. 26.32838 Lakhs
Interest as on 1-04-2015 |  |  |  | Rs.4.14928 Lakhs
S.No | DDO,s | Funds Released( In Lakhs) |  |  | Funds Utilized In Lakhs) |  |  | Bills remained pending in the treasuries for drawal | Interest as on 1-04-2015
|  | Treasury Drawal | Cheque Drawal | Total | Treasury Drawal | Cheque Drawal | Total
1 | CAO Jammu | 7.226 | 0.7 | 7.926 | 1.1276 | 0.533 | 1.6606 | 5.0154 | 0.51086
2 | CAO Samba | 7.4 | 0.2 | 7.6 | 2.65 | 0.2 | 2.85 | 4.75 | 0.0009
3 | CAO Kathua | 7.774 | 0.2 | 7.974 | 5.024 | 0.2 | 5.224 | 2.75 | 0.24449
4 | CAO Rajouri | 7.8 | 0.7 | 8.5 | 3.25 | 0.7 | 3.95 | 4.543 | 0.03959
5 | CAO Poonch | 7.95 | 0.2 | 8.15 | 7.14 | 0.2 | 7.34 | 0 | 0
6 | CAO Udhampur | 5.9 | 0.2 | 6.1 | 3.9 | 0.2 | 4.1 | 2 | 0.05886
7 | CAO Reasi | 7.13 | 1.2 | 8.33 | 2.68 | 1.2 | 3.88 | 4.65 | 0.04028
8 | CAO Ramban | 7.2 | 0.2 | 7.4 | 7.2 | 0.2 | 7.4 | 0 | 0.00565
9 | CAO Doda | 6.23 | 0.2 | 6.43 | 4.25 | 0.2 | 4.45 | 1.5 | 0.00537
10 | CAO Kishtwar | 6.65 | 0.2 | 6.85 | 5.9 | 0.2 | 6.1 | 0 | 0
11 | Joint Director Agriculture (Inputs) | 0 | 1.85 | 1.85 | 0 | 1.85 | 1.85 | 0 | 2.0281
12 | Accounts Officer | 1.12 | 2.8961 | 4.0161 | 0 | 2.8961 | 2.8961 | 1.12 | 1.2046
13 | Dy. Dir. Trgs | [7 empty] | 0.01054
13 | Total | 72.38 | 8.7461 | 81.1261 | 43.1216 | 8.5791 | 51.7007 | 26.3284 | 4.1493